## UAT - CAPM
Project : | iMerchant Banking - User Acceptance Testing (UAT) |  | INSTRUCTIONS:
Customer: | CAPM Advisory Ltd |  | Please go through each of the cases and follow the steps. If you get the expected outcome as suggested in the [Expected Result]
Prepared By : | BOSL Development Team, CMD |  | and in order to be confirmed with the result please check the [Confirmation] column. Once confirmed, select Yes in the [Passed]
Contact Person: | Md. Nazmul Ahsan |  | If you have not received the expected result as suggested, then select No and mention the result with details in the [Remarks] column.
Date : | 2014-04-09
Test Case ID | Title | Steps (Description) | Expected Result | Confirmation | Passed | Remarks | Tested By | Resource
CAP001 | Creating new investor | Go to Portfolio > Complete Profile> New to add new investor manually OR new investor created from CDBL Import Routine automatically. | New investor created either from complete profile or from CDBL Import Routine. | Type Account Number in the Complete Profile OR in the Investor Summary Dashboard and press ENTER. The investor details will be shown.
CAP002 | Deduct Opening Fee(s) during new account opening | Click YES when the software prompts user whether to deduct Account Opening Fee when adding investor manually from Complete Profile. | Opening Fee(s) will be deducted when new investor is created either from Complete Profile or CDBL Import Routine. | Check the investor ledger statement from the Reports > Investor > Investor Ledger Statement.
CAP003 | Create IDA Account | Go to Portfolio > Margin Accounts > New Account (Enter AC Number press enter button then select margin category then Save) | The selected NDA Account will be updated to IDA provided the account has been created since the IDA Activation days that can be set from Settings > Housekeeping > Margin Category | Type the account number in the Investor Summary Dashboard and press ENTER. The investor information will be shown with the Account Type set to IDA.
CAP004 | Investor Portfolio | Report > Report View > Investor (Select from module dropdown) > Investor Portfolio Statement (select from table)> Enter Account number and Date | Investor Portfolio Statement report will be loaded. | All the figures should be calculated correctly as per the formulae acknowledged by the Customer.
CAP005 | Import Approved Security List (Optional) | Trade Management > Approved Instrument Select CSV File then click import (File format has been provided) | CSV file will be imported successfully and instrument will be updated accordingly. | Go to Settings > Housekeeping > Instruments
CAP006 | Cash Limit Generation | Go to Trade Management > Cash Limit > Click APPLY to load the limits. Select Panel Broker > Select the list investors to generate the limits for the selected panel broker and finally click on GENERATE to save the cash limit file. | Cash limit file will be generated according to the purchase power. Purchase power is calculated based on the formula acknowledged by the Customer | Open the Cash Limit file from the directory where it is saved. The file should be generated in the format compliant to the Trading Software.
CAP007 | Share Limit Generation | Go to Trade Management > Share Limit > Click APPLY to load the limits. Select Panel Broker > Select the list investors to generate the limits for the selected panel broker and finally click on GENERATE to save the share limit file. | Share limit file will be generated according to the matured balance. | Open the Share Limit file from the directory where it is saved. The file should be generated in the format compliant to the Trading Software.
CAP008 | Import Price file | Go to Trade Management > Price Import > Select DSE price file > Click Import. | The last trading price of the instruments will be updated. | Go to Settings > Housekeeping > Instruments and check Market Price. Type the account number in the Investor Summary Dashboard and press ENTER. Check the Market Price in the Instrument List of the Portfolio
CAP009 | Import Trade (DSE) | Go to Trade Management > Import Trade > Select Stock Exchange > Select Panel Broker > Select the trade file from the Panel Broker > Click Import | The software will import the trades and load them in a form with status PENDING that suggests that they need to be processed once confirmed by the user. The software will validate the following: 1. Investor Account Number does not exist. 2. Investor BO Number does not exist. 3. Instrument does not exist (most likely for new instrument which need to setup from Settings > Housekeeping > Instruments.) 4. Non-Margin instruments bought You may filter the trade list by Panel Broker, Account Code, Instrument, Transaction Type. | Check from the Investor Summary Dashboard if the Investor with valid Account Number and BO Number exists. Check from Settings > Housekeeping > Instruments if the Instrument exists. Verify the trading reports from the Reports > View Reports > Housekeeping > House Income Statement (Clientwise/Datewise)
CAP010 | Import Trade (CSE) | Go to Trade Management > Import Trade > Select Stock Exchange > Select Panel Broker > Select the trade file from the Panel Broker > Click Import | The software will import the trades and load them in a form with status PENDING that suggests that they need to be processed once confirmed by the user. The software will validate the following: 1. Investor Account Number does not exist. 2. Investor BO Number does not exist. 3. Instrument does not exist (most likely for new instrument which need to setup from Settings > Housekeeping > Instruments.) 4. Non-Margin instruments bought You may filter the trade list by Panel Broker, Account Code, Instrument, Transaction Type. | Check from the Investor Summary Dashboard if the Investor with valid Account Number and BO Number exists. Check from Settings > Housekeeping > Instruments if the Instrument exists. Verify the trading reports from the Reports > View Reports > Housekeeping > House Income Statement (Clientwise/Datewise)
CAP011 | Pay In (Settlement) | Go to Depository > Pay IN > DSE Pay IN/CSE Pay In > Select Save location > Generate | 1. System will show all Pay In record for current business date 2. Pay IN file will be generated in the location selected. | Open the Pay In file from the location it is saved. The file should be generated in the format compliant to CDBL.
CAP012 | Trade Process (DSE) | Go to Trade Management > Trade File > Select the Trade file from the list and Click Show Details > Select the Stock Exchange as DSE >Process Trade. IMPORTANT: This a one time operation and will take some time and it is highly recommended that you close all the open windows of the software before initiating the process and no other users enter any investor related transactions during the process. However, the users may view reports and enter in-house transactions. | The software will process all the trades and status will be changed to POSTED from PENDING. Trade processing means the trades are acknowledged by the users and ready to be finalized by the software. Once the trades are processed: 1. The portfolio of the investors related to the trades are updated and the trades are locked (POSTED) suggesting that they cannot be altered. 2. The Payable/Receivables journals to Panel Brokers, the income journals like commission, the expense journals like broker commission are posted to General Ledger (GL). | Check Investor Portfolio Statement from the Reports > View Report > Investor > Select Investor Portfolio Statement and Investor Ledger Statement from the list > Type Account number and press ENTER. You may also view the investor portfolio from the Investor Summary Dashboard. Check the General Ledger Report for Payable to Clients, Payable/Receivable to [Panel Broker Name], Broker Commission Expense, Commission Income etc from the Reports > View Report > Financial > Select the Date Range> Double click on General Ledger from the list > Browse the Nominal Account from the list and click OK. Check the Client Account Balances reports from Reports > View Report > Financial > Select the Date > Select Client Accounts Payable/Receivable/Client Accounts Status/Client Account Status Details and Click Generate
CAP013 | Trade Process (CSE) | Go to Trade Management > Trade File > Select the Trade file from the list and Click Show Details > Select the Stock Exchange as CSE >Process Trade. IMPORTANT: This a one time operation and will take some time and it is highly recommended that you close all the open windows of the software before initiating the process and no other users enter any investor related transactions during the process. However, the users may view reports and enter in-house transactions. | The software will process all the trades and status will be changed to POSTED from PENDING. Trade processing means the trades are acknowledged by the users and ready to be finalized by the software. Once the trades are processed: 1. The portfolio of the investors related to the trades are updated and the trades are locked (POSTED) suggesting that they cannot be altered. 2. The Payable/Receivables journals to Panel Brokers, the income journals like commission, the expense journals like broker commission are posted to General Ledger (GL). | Check Investor Portfolio Statement from the Reports > View Report > Investor > Select Investor Portfolio Statement and Investor Ledger Statement from the list > Type Account number and press ENTER. You may also view the investor portfolio from the Investor Summary Dashboard. Check the General Ledger Report for Payable to Clients, Payable/Receivable to [Panel Broker Name], Broker Commission Expense, Commission Income etc from the Reports > View Report > Financial > Select the Date Range> Double click on General Ledger from the list > Browse the Nominal Account from the list and click OK. Check the Client Account Balances reports from Reports > View Report > Financial > Select the Date > Select Client Accounts Payable/Receivable/Client Accounts Status/Client Account Status Details and Click Generate
CAP014 | Fund Deposit/Withdraw Entry | Go to Cashbook > Investor Account > Select Deposit or Withdraw Tab. It will show a list of deposits or withdrawal transactions entered. The list can be filtered by Account Number, Status, Date Range, Receipt Type, Reconciled etc. Click on New to enter a new transaction. An entry form will appear. Select the Bank Account from the dropdown at the top > Enter the account number and press ENTER > Enter all the mandatory fields and Press ENTER. | The Amount entered will be shown in Words below. A message will be shown suggesting that the transaction has been entered successfully. The software will prompt the user whether to print the Receipt/Voucher. Upon closing the Entry form, the transaction newly entered will be shown in the list with a status PENDING suggesting that the transaction has not been authorized yet and can be modified. | Check Investor Portfolio Statement from the Reports > View Report > Investor > Select Investor Portfolio Statement and Investor Ledger Statement from the list > Type Account number and press ENTER. You may also view the investor portfolio from the Investor Summary Dashboard. Check the General Ledger Report for Payable to Clients, Consolidated Bank Account from the Reports > View Report > Financial > Select the Date Range> Double click on General Ledger from the list > Browse the Nominal Account from the list and click OK. Check the Client Account Balances reports from Reports > View Report > Financial > Select the Date > Select Client Accounts Payable/Receivable/Client Accounts Status/Client Account Status Details and Click Generate
CAP015 | Bank Payments/Receipts Entry | Go to Cashbook > Bank Pay/Rec > Select Payment or Receipt Tab. It will show a list of transactions entered. The list can be filtered by Status, Date Range etc. Click on New to enter a new transaction. An entry form will appear. Select the Bank Account from the dropdown at the top > Select the corresponding Nominal Account > Enter all the mandatory fields and Press ENTER. | A message will be shown suggesting that the transaction has been entered successfully. The software will prompt the user whether to print the Voucher. Upon closing the Entry form, the transaction newly entered will be shown in the list with a status PENDING suggesting that the transaction has not been authorized yet and can be modified. | Double click on the transaction and it will opened in the editable mode.
CAP016 | Posting Financial Transaction | Go to Cashbook > Investor Account OR Bank Pay/Rec > Select any of the tabs Select a transaction with a status PENDING and Click on Update To Ledger. | A message will be shown saying that the selected financial transaction is posted and updated to General Ledger. The status will be changed to POSTED suggesting that the transaction is posted to GL and will not be allowed to modify. If the transaction is already posted or cancelled, the software give a message. | Check the General Ledger Report for Bank Accounts from the Reports > View Report > Financial > Select the Date Range> Double click on General Ledger from the list > Browse the Nominal Account from the list and click OK.
CAP017 | Cancelling Financial Transaction | Go to Cashbook > Investor Account OR Bank Pay/Rec > Select any of the tabs Select a transaction and Click on Cancel Transaction | If the selected transaction is already Posted to GL, a message will be shown asking the user to confirm whether to go ahead with cancelling the transaction. If the user confirms, a reversal journal will be entered in to the GL. If the selected transaction is PENDING, then the transaction will be marked as REJECTED. | Check the General Ledger Report for Bank Accounts from the Reports > View Report > Financial > Select the Date Range> Double click on General Ledger from the list > Browse the Nominal Account from the list and click OK.
CAP018 | Day Start | Settings (Top Right hand side) > Calendar (Left Menu) > Working Calendar > Click Day Start | This will make software to be ready to run on a new working or business date. During the day start process, the daily fees/charges and interests are calculated and accrued as below: 1. IDA account which are using margin fund will accrued interest, interest amount figure is showed correct. 2. All account will be accrued management fee based on NAV/Equity. Net amount figure will be shown correct. | The current business date will be shown in the dashboard. Go to Report > Report View > Margin (Select from module dropdown) > Select a report > Select Date > Double click on row/ Click Generate > to view the accrued Daily Margin Interest or Daily Management Fee
CAP019 | Day End | Settings (Top Right hand side) > Calendar (Left Menu) > Working Calendar > Click Day End > Click Confirm | This will close the current working date and lock the date therefore not allowing any further entries. During the Day End process, the software will: 1. Run a thorough diagnosis to ensure there are no anomalies in the system. 2. Take a backup of the data. 3. Generate and automatically send the MIS reports to the management. | Login to the software after the day end process and the user should find all the menus except the report disabled.
CAP020 | Bank Reconciliation | 1. Settings (Top Right hand side) > Calendar (Left Menu) > Working Calendar > Click Bank Recon. 2. Select Bank > Select Cashbook A/C > Select Transaction > Reconcile > Save | Bank reconciliation will be saved successfully | Check the unclear cheque figure in the Investor Portfolio Statement.
CAP021 | Import CDBL File | Depository > Import CDBL File > Select CDBL folder (Folder must contain below report txt file) > Import 1. DP01 2. DP70 3. DP64 4. DP42 5. DP52 6. DPA6 | 1. Check BO Confirmation Report in CDBL module 3. Check Investor Portfolio Statement where it will show the corporate action receivable in the bottom of the report. 4. Check client ledger statement where CDBL charge has been deducted from the client ledger. | Check CDBL Import Log from Depository > Import Detail Log
Yes
No